## Sheet1
Task | Comments | Description
Order Management | Done -Tampa (based on a file shared by Mika) | Automatically create sales orders in NS from ebay
Inventory Management | 1. Created Inventory Item and Populated the HTML description 2. Did not manage to publish offers due to the lack of access 3. Stock Quantity update is done for Tampa (on fulfillment and receipts) | Updating eBay Inventory
Error Handling and scalability | Error handling: Done through Queues. Scalability: we need to know the structure of business for that (in case of multiple stores..etc)
Phase1
Configure eBay dev account and obtain credentials | Done
Setup NS Sandbox with scripts | Done
Create Custom Records In NetSuite | Done
Sync Queue Record | Done
eBay ID's connected to products Id's | Currently it uses the SKU of the item, please let us know if something else is required
Both Phase1 Milestones are done
Phase2
Auth Token Script | Done
Sync List Updater | Done, used configuration record
Order Sync Script | Done, feedback is needed
Queue Writer Script | Done, UE script on Item record
Product/Inventory Sync Script | MR script done
Fulfillment Script | Not done, need samples and the logic behind it (We have no access)
*All scripts are supposedly deployed
Product Initialization and Updates | Need some elaboration to make sure whether we've done this or not
Inventory Synchronization Development | Need some elaboration to make sure whether we've done this or not
Error handling | Done, through queues
Retry mechanism | Code exists but not deployed, will be deployed at last (Should it be on queue level as a button or a scheduled job?)
Testing | Our work is test-driven. But we will conduct a full cycle test once the units are done
Milestones for phase 2: Partially done, for the units we have finished only
Phase 3
Simulate real-workd scenarios: Pending on having real data
Phase 4
Will be initiated and done, once all the previous phases are done and confirmed