## Sheet1
System has to track due dates - and x days from due date, system has to ensure that stock is either reserved, or a procurement order is being processed for fulfillment | sales manager depened on the team | 1 approval | PO and quotation | possible for mutli brand
We will create a flag on PO so user can change it when acknowledgement is done | before flagged the order be as draft | 1 flag with 1 attachement mandatory | add Draft word of the PO form and remove once flagged
sample request type per location and approval - sales rep- and sales manager to approve based on the sales rep, national sales manager- finance manager - changed | to be received from PAN and suggeist our one | one approval on sales line (brand) | then on amount (predefined automated)
define new department per customer and link it on customer record, and add it to lead, estimate, and sales order | hussam | 1 contact one department
sales price list Pan Arabia to get back to us and warning if sales price for private not less than nupco prices. | if less than nupco price rejected | system to reject the line if price is less than nupco or minimum of nupco | if order has any item as gift or zero price , the order must be approved by on person - supervisor by product line | add check box of this item as gift or nut
on quotation add flied for a number of delivery days, notification before delivery date before 30 days and before 30,15 and 5 days 3 notification | sales order | entry as date | weekly notification on sales order for the due date - number of days and date | all involved - sales rep , product line manager - chief of logistics - chief of finance
all sales order will be approved by sales coordinator to save sales order withhout source documents(except cash order). | all mandatory except cash order | no approvals | one file
on quotation we need to compare the lead time of the supplier per item with the number of days if exceeded need to be approved by the chief logistics(Only for suppliers with lead times exceeding 90 days.) | no need
sales order type (blanked sales order, planned sales order, standard sales order.) | hussam
Sales order • if exceeds 90 days -the finance manager • credit limit also finance manager | normal cycle | depened on payment term and CL
Journal Entry 2 levels- first level entry, 2nd level senior accountant, 3rd finance manager. | no need for WF one create and one post
approval for expense entry, sales manager, seniors’ accountant. | entry - supervisor approval - finance approve to apply | as standard
For blanket POs, an alert has to be created once the last release is used more than 90 days ago - Alert goes to sales manager, Sales rep, accountant - it doesn't go away except with invoicing. | alert 90 days - weekly after 90 | all involved - sales rep , product line manager - chief of logistics - chief of finance
System has to send an alert to the client on due date, and also notify involved company employees (Collection, Sales Rep, Sales Manager, Finance) - The system has to open a task that doesn’t close except with the full payment of the due amount. | AR ageing | due date and weekly | all involved - sales rep , product line manager - chief of logistics - chief of finance and CEO
type SO planned and notification before delivery date before 30 days and before 15 and 5 days 3 notification. | no need - only on quotation
RMA will be entered by sales team and approved by sales manager then senior accountant | depened on brand for sales manager
journal voucher approval • 2 levels- first level entry, 2nd level senior accountant, 3rd finance manager. we will use expense management | repeated
approval for expense entry, sales manager, seniors’ accountant. | repeated
For SFDA we will define WH called SDFA and when released to transfer to main WH or define status hold for SDFA | add attachement manadory for SFDA WH
For blanket POs, an alert has to be created once the last release is used more than 90 days ago - Alert goes to sales manager, Sales rep, accountant - it doesn't go away except with invoicing. | repeated
add field item per line code name | free text with add new
Integration to Zatca phase 2 |  |  | 20 | VS

## Sheet2
System has to track due dates - and x days from due date, system has to ensure that stock is either reserved, or a procurement order is being processed for fulfillment | Alaa | Pending / Need Info from Pan
We will create a flag on PO so user can change it when acknowledgement is done | Hamza | ready
sample request type per location and approval - sales rep- and sales manager to approve based on the sales rep, national sales manager- finance manager - changed | Hamza | ready
define new department per customer and link it on customer record, and add it to lead, estimate, and sales order | Hussam
sales price list Pan Arabia to get back to us and warning if sales price for private not less than nupco prices. On (SO, Estimate), Rate must be less than Nupco price | Hamza | ready
on quotation add flied for a number of delivery days, notification before delivery date before 30 days and before 30,15 and 5 days 3 notification, I need emails from Pan team | Hamza | ready
all sales order will be approved by sales coordinator to save sales order withhout source documents(except cash order). | Hamza | ready
on quotation we need to compare the lead time of the supplier per item with the number of days if exceeded need to be approved by the chief logistics(Only for suppliers with lead times exceeding 90 days.)
sales order type (blanked sales order, planned sales order, standard sales order.) | Hussam
Sales order • if exceeds 90 days -the finance manager • credit limit also finance manager | Alaa | Done/ Neeed SB Access
Journal Entry 2 levels- first level entry, 2nd level senior accountant, 3rd finance manager.
approval for expense entry, sales manager, seniors’ accountant.
For blanket POs, an alert has to be created once the last release is used more than 90 days ago - Alert goes to sales manager, Sales rep, accountant - it doesn't go away except with invoicing. | Hamza | Done/ Neeed SB Access
System has to send an alert to the client on due date, and also notify involved company employees (Collection, Sales Rep, Sales Manager, Finance) - The system has to open a task that doesn’t close except with the full payment of the due amount. | Alaa | Pending
type SO planned and notification before delivery date before 30 days and before 15 and 5 days 3 notification.
RMA will be entered by sales team and approved by sales manager then senior accountant | Alaa | Done/ Neeed SB Access
journal voucher approval • 2 levels- first level entry, 2nd level senior accountant, 3rd finance manager. we will use expense management
approval for expense entry, sales manager, seniors’ accountant.
For SFDA we will define WH called SDFA and when released to transfer to main WH or define status hold for SDFA | Hamza | ready
For blanket POs, an alert has to be created once the last release is used more than 90 days ago - Alert goes to sales manager, Sales rep, accountant - it doesn't go away except with invoicing.
add field item per line code name, on SO and Estimate | Hamza | Done/ Neeed SB Access
Integration to Zatca phase 2 | Alaa | Done/ Neeed Info from Pan

## Sheet3
Points | Consultant | Notes | Status
Quotation - Form | Hamza | * Image alignment in center. (DONE) * Designation is the quot ID. (DONE) * Shlef Life spelling. (DONE) * Remove customer number from cust name. (Pending Functional) * Reference number must be field in estimate record and filled by user. (DONE) * Cost/each replace with price. (DONE) * Arabic description for item below product description. (DONE) * Each page have one item. (DONE) * Add total tax and total value in the last page. (DONE) * In item table must add discount field. (Discount in estimate level) * Add total discount in header table. (DONE) * Remove the middle column in header table. (DONE)
Sample Request - Form | Hamza | * Dispensed to: is custom field list of contacts and filled by user. (DONE) * Cost Center from pan team. (DONE, pending functional team to import data) * Cost/Unit replace it with price/unit. (DONE) * Request for and unit columns will be in the header table not item table (DONE) * Item reference must be replaced by item ID. (DONE) * Purpose drop down list custom field provided by pan team. (DONE, pending functional team to import data) * replace Total Release Value with total sample (DONE)
So Blanket - Form | Hamza | * Item Ref replace it with Item ID. (DONE) * Replace type Cash with Planned/Blanket. (DONE) * release number must generate a sequance number based on number of fulfillments. (Need to check with omar) (DONE) * release sequance (number of the last ite mfulfillment). (Need to check with omar) (DONE)
SO Cash - Form | Hamza | * remove status row in header table. (DONE) * replace item ref with item id. (DONE) * replace Total Release Value with total SO. (DONE) * Bank Transfer must be document attached as source link. (Need to check with omar)
SO Standard - Form | Hamza | * change the type value to standard. (DONE) * buyer must be contact. (DONE) * replace Total Release Value with total so. (DONE) * check Unit Price replace Item Ref with Item ID. (DONE)
PO - Form | Alaa | * Add Amount in words, * remove red color in item tables, * replace order type with order status , * change ID to Reference number
Tax Invoice - Form | Alaa | * add discount per item and total discount, * add nupco descrion on invoice level for add nupco data checkbox, * so if it is checked in the item list will show nupco code and nupco description , if it is not checked it will show item desc only with out nupco, (fields is Nupco Description , Nupco code , MOH Code , Customer reference), * add UOM in line level, * (will receive invoice form from pan arabia team and merge data with old one) check with functional team about the production date and expiration date and lot number if it can be generated automatically * fix customer address in arabic
Delivery Note - Form | Alaa | * check delivery note if we can generate delivery note without SO and then attach SO with it later, * remove unused data fields
Create a flag on PO record (ACKNOWLEDGEMENT field if checked, file attachment will be mandatory and when prinitng form will show if its draft or not) | Hamza
Sample Request Record, form, and Approval workflow | Hamza | * Remove sales rep approval keep only sales manager. (DONE)
Add Nupco Price on line level for SO and Quotation record, if the Item Rate is less than NUPCO Price an alert will pop up to notify user to change item rate | Hamza | * Remove Gift column in so and estimate, if rate is 0 then igonre the nupco price. (DONE)
On SO Record send emails based on delivery days field if the SO is not Fulfilled yet, (Need Users from Pan, I have roles but not the users) chief of logistics, createor and sales manager of the class | Hamza
WorkFlow on all SO Type, attachment will be mandatory for cash sale so only | Hamza
An Email will be sent for Blanket PO (if the PO is not received yet and if the PO is partially received), (Need Users who will receive emails from Pan team), reminder in SO for blanket so | Hamza | * Replace this from PO to SO
Define SFDA Warehouse, when user try to make Item receive and the item is in the SFDA warehouse the status in inventory details will be on Hold | Hamza
Add Sublist field on SO and Quotation Record named Nupco code, it must be a list and the user can define new code and it will be saved in the list | Hamza | * Add below fields for so and estimate (fields is Nupco Description , Nupco code , MOH Code , Customer reference). (DONE)
Sales orders must be approved by finance manager if the customer exceeds the credit limit or has an open invoice exceeding the due date. | Alaa
RMA will be entered by sales team and approved by sales manager then senior accountant | Alaa
The system will send weekly email alerts to remind employees of open invoices' due dates. | Alaa
The system has to track due dates - and x days from the due date, the system has to ensure that stock is either reserved, or a procurement order is being processed for fulfillment | Alaa
Integration with Zatca phase 2 | Alaa